18 December 2014

WEEKLY COMMUNICATIONS UPDATE

Overview

- Seven new houses in Obrenovac, Krupanj and Paraćin have been constructed so far, while 331 flood affected homes have been renovated in Obrenovac, Krupanj, Šabac, Bajina Bašta, Šid, Loznica, Smederevska Palanka, Velika Plana, Čačak, Ub and Koceljeva. The private housing reconstruction process for the total of some 950 in 30 municipalities funded through the European Union Assistance for Flood Relief in Serbia Programme is underway. Depending upon the weather conditions, the completion of this intervention is expected during December 2014 and January 2015.

- Delivery of the animal feed to more than 1,600 agriculture producing families should commence in the week of 22 December 2014. Each producer will receive 320 kilograms of cattle, poultry and pig feed in order to restore agriculture production and own income generation.

Implementing Partner: ASB/HC/IDC/DIVAC

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Valjevo | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 16 Housing Units reconstruction: Works on 12 houses are in finishing phase, in 4 houses are in progress Finishing of reconstruction works planned within approx 2 weeks. - 9 new brick Housing Units: 3 houses are in construction, 5 houses are in preparation phase and in 1 house works did not start yet. Due to the weather conditions (snow) the houses will not be completed by the end of this year. Economic Component - Distribution of building material completed and distribution of IG Grants ongoing Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures - Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Osecina | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 25 Housing Units reconstruction: works on 10 houses are finished, in progress 15 houses (80% of works are done) Finishing of reconstruction works planned within approx 2 weeks. Economic Component - Continue the distribution of IG grants and complete distribution of building material Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU - Continue distribution of IG Grants | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Mali Zvornik | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 15 Housing Units reconstruction: Works on 11 houses are in finishing phase, in 4 houses are in progress. Finishing of reconstruction works planned within approx 2 weeks. - 1 new Housing Unit: House is in finishing phase, interior works and setting the laminate still to be done All interior installations are done Finishing of construction works planned within approx 2 weeks. Economic Component - Continue the distribution of IG grants and complete distribution of building material Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU - Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljubovija | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 17 Housing Units reconstruction: Works on 12 houses are in finishing phase, in 5 houses are in progress (80% of works are done) Finishing of reconstruction works planned within approx 2 weeks. - 6 Housing Units construction: works are ongoing Finishing of construction works planned within approx 3 weeks. Economic Component - Continue the distribution of IG grants and complete distribution of building material Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU - Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sabac | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 28 Housing Units reconstruction: works on 8 houses are finished, in progress on 20 houses (70 - 80% of works are done) Finishing of 20 houses planned within approx 2 weeks. Economic Component - Continue the distribution of IG grants Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU - Continue distribution of IG Grants | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) |
| Bajina Basta | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: works on 15 houses are finished; Finishing of the houses planned for next week. - 5 Housing Units construction: Construction of 5 houses is in finishing phase, interior works and setting the laminate still to be done All interior installations are done. Finishing of 5 houses planned within approx 2 weeks Economic Component - Continue the distribution of IG grants Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sid | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on 1 house are finished; works on 12 houses are in finishing phase; works on 19 houses are in progress (70% of works are done, interior works and setting the laminate still to be done, the biggest obstacle is humidity); Finishing of houses planned within approx 2/3 weeks - 5 Housing Units construction: Construction of 1 house is in finishing phase (works on facade and interior works ongoing); 4 houses got the roof Finishing of houses planned within approx 2/3 weeks Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) |
| Loznica | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) -20 Housing Units reconstruction: Works on 5 houses are finished (without setting laminate); Works in finishing phase on 14 houses ( 90% of works are done, setting the laminate still to be done, the biggest obstacle is humidity); Works on 1 house are in progress ( 60% of works are done, the biggest obstacle is extremely humidity; Finishing of houses planned within approx 2/3 weeks - 9 Housing Units construction: 4 houses got the roof and for 2 houses all material is delivered; start of the construction of 3 new houses All houses planned for finishing by the half of January 2015 Economic Component - Continue distribution of IG grants Plan for the next week - Signing of the contract for furniture and appliances after the prior approval of DEU - Continue the distribution of IG grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |

Date of Update: 18/12/2014

Implementing Partner: Danish Refugee Council – DRC with Eneca

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR FINAL BENEFICIARIES INCLUDING THE END TIMEFRAME |
| --- | --- | --- |
| Smederevska Palanka | - Reconstruction of individual housing objects (DRC): - Reconstruction process is neering its completion. | The reconstruction works are ongoing in all 20 houses, out of which 10 have been completely repaired and ready for the family move-in. |
|  | - Construction of prefabricated houses (DRC): - The construction process is ongoing and is proceeding according to the action plan. | The construction works are in the progress in all 3 prefabricated houses. Out of which one house has been brought to the roof and on the other one prefab elements are being installed. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture has started this week. | Household appliance and furniture items have been provided to 2 beneficiary families. |
|  | - IGA component (Eneca): - The Local Open Tender is ongoing until 19 Dec 2014. | Eneca has contracted the best quality suppliers of necessary business equipment and processing material. |
| Velika Plana | - Reconstruction of individual housing objects (DRC): - The reconstruction process has been brought to the end. | The reconstruction works in all 12 houses are finished creating necessary conditions for the handover of works to be realised in the beginning of the following week. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is in preparatory phase. | Household appliance and furniture items will be provided to the beneficiary families 20 Dec onwards. |
|  | - IGA component (Eneca): - The Local Open Tender is ongoing until 19 Dec 2014. | Eneca has contracted the best quality suppliers of necessary business equipment and processing material. |
| Cacak | - Reconstruction of individual housing objects (DRC): - Reconstruction process is neering complition. | The reconstruction works in all 14 houses have been brought to the final phase, out which 10 houses were completely reconstructed, whilst the other four will be finished in the following week. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is in preparatory phase. | Household appliance and furniture items will be provided to the beneficiary families 20 Dec onwards. |
|  | - IGA component (Eneca): - The Local Open Tender is ongoing until 19 Dec 2014. | Eneca has contracted the best quality suppliers of necessary business equipment and processing material. |
| UB | - Reconstruction of individual housing objects (DRC): - The reconstruction process has been brought to the completion phase. | The reconstruction works are ongoing in all 23 houses, out of which 10 houses have been completely reconstructed, whilst the ramaining number will be 50% finalised in the following week. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is in the preparatory phase. | Household appliance and furniture items will be provided to the priority beneficiary families 20 Dec onwards. |
|  | - IGA component (Eneca): - The Local Open Tender is ongoing until 19 Dec 2014. | Eneca has contracted the best quality suppliers of necessary business equipment and processing material. |
| Koceljeva | - Reconstruction of individual housing objects (DRC): - The reconstruction process has been brought to the completion phase. | The reconstruction works are ongoing in all 25 houses, out of which 10 have been completely reconstructed. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is in the preparatory phase. | Household appliance and furniture items will be provided to the priority beneficiary families 20 Dec onwards. |
|  | - IGA component (Eneca): - The Local Open Tender is ongoing until 19 Dec 2014. | Eneca has contracted the best quality suppliers of necessary business equipment and processing material. |
| Jagodina | - Reconstruction of individual housing objects (DRC): - The reconstruction process has been brought to the completion phase. | Out of the total number of 33 houses selected for the reconstruction component, 60% have been completely reconstructed. |
|  | - Construction of prefabricated houses(DRC): - The construction site has been prepared and the administrative conditions have been realized enabling the commencement of construction works by the end of December 2014. | Foundation and floor slab will be constructed, creating necessary conditions for gradual installation of prefab elements by the end of January 2015. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is in preparatory phase. | Household appliance and furniture items will be provided to the priority beneficiary families 20 Dec onwards. |
| Paracin | - Reconstruction of individual housing objects (DRC): - The reconstruction process has been brought to the completion phase. | In the current week 50% of all 43 houses have been completely reconstructed, estimating the increase of 35% of works completed in the following week. |
|  | - Construction of prefabricated houses(DRC): - The construction process is nearing the completion in the majority of houses. | The construction works are ongoing in all 9 houses, out which 3 are completely constructed and ready for the family to move-in. Remaining 6 houses are in the final phase of finishing works. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is in the preparatory phase. | Household appliance and furniture items will be provided to the priority beneficiary families 20 Dec onwards. |
|  | - IGA component (Eneca): T The Local Open Tender is ongoing until 19 Dec 2014. | Eneca has contracted the best quality suppliers of necessary business equipment and processing material. |

Date of Update:	18  December 2014

Implementing Partner:Help – Hilfe zur Selbsthilfe e.V.

Overview:

Reconstruction works:

Reconstruction works for total of 51 beneficiaries chosen in the first lot (10 in Kraljevo, 15 in Lazarevac, 15 in Svilajnac, 5 in Trstenik and 6 in Varvarin) . Flooring is in progress and interior doors installation, all works expected to be finished by 25 December.

Works on additional 94 houses in all municipalities have begun on 1 December 2014 and will be finished in 50  calendar days.

Value of works for the first 51 beneficiary is 162.767,62 EUR while the total available budget for reconstruction amounts to 780.000,00 EUR.

Prefabricated houses: The works on 8 prefabricated houses in Svilajnac and 1 in Varvarin in the final phase, expected to be finished by the end of December.

Value of the works in progress 151.500,00 EUR.

Contract have been signed with the contractor for 6 more prefabricated houses (2 in Svilajnac and 4 in Lazarevac) in the value of 146.990,00 EUR. Works expected to commence by 20 December.

Household appliances and furniture: Procurement procedure of household appliances and furniture for 162 beneficiaries is in progress and delivery is foreseen 22 December depending on the reconstruction/construction of houses works completion.

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT ANDa) STAGE OF COMPLETION AND b)TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| KRALJEVO | Reconstruction works in value of 29.022.74 EUR for 10 houses in Kraljevo in the final phase of inner finishing works: installation of interior doors and flooring. Works on additional 8 houses have started. Procurement procedure of 20 furniture sets is in progress, with delivery anticipated from 25 December. Tender for IGA component announcement on 19 Dec. | At least 10 homes repaired and at least 10 families provided with the basic furniture and household appliances. At least 20 micro and small business provided with equipment, spare parts and business facilities renovated. |
| KOSJERIC | On 3 November 12 beneficiaries in Kosjeric, village Seca Reka received 39800 raspberry seedlings. Value of the assistance: cca 11.000,00 EUR (1313400 dinara). | At least 10 micro and small businesses supported by the raspberry seedlings, equipment spare parts and renovated business facilities. |
| LAZAREVAC | Reconstruction works on 15 houses in Lazarevac, in value of 38.020,81 EUR, from the first lot in the finishing phase, interior doors installation in progress, completion 22 December. Procurement procedure for 30 furniture in progress, delivery from 25 Dec. Tender announcement for IGA component on 19 December. | At least 30 families provided with the construction material sets and priority works; at least 36 beneficiaries provided with the basic furniture and household appliances, at least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| SVILAJNAC | Reconstruction works on 15 houses and 8 prefabricated houses in Svilajnac in the finishing phase, interior door installation on/from 24 Dec, pending: works on pavement, septic tank and inspection chamber from 20 December followed by the water and electricity connection. Deadline 25 December. Works on 22 houses begun last week, and the rest of 37 expected to begin in the fourth week of December. Procurement procedure of 77 furniture sets in progress, deliveries expected in the last two weeks of December. Tender announcement for IGA component on 19 December. | At least 70 construction material sets with priority works delivered; At least 78 sets of basic furniture and household appliances supplied, eight families provided with the prefabricated houses; At least 23 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| TRSTENIK | Reconstruction works on 5 houses in the inner finishing phase, flooring and inner doors placement, deadline 22 December. Launched works on 8 more houses to be finished by the end of January. Procurement procedure of 10 furniture sets in progress. Delivery throughout second half of December. | At least 5 households supported by the construction material sets with priority works, At least 5 households provided with the basic furniture and appliances sets, At least 15 micro and small businesses provided with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| VARVARIN | Reconstruction works on 6 houses in Varvarin in the finishing phase: flooring in progress and interior doors placement next week. All works expected to be finished on 23 December. Procurement procedure of 8 furniture sets in progress, pending delivery. Tender announcement for IGA component on 19 December. | At least 5 families supported by the construction material sets with priority works. At least 6 families supported by the basic furniture and household appliances. One family supported by provision of prefabricated house, At least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |

Date of Update: 18/12/2014

Implementing Partner: IOM

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Krupanj | About 0.2 M investments. 195 houses were planned out of which 193 finished. Out of 193 houses 44 finished by the beneficiaries themselves. Finishing works underway. | Commencement of the works in the first week of October. 195 houses to be repaired, but some houses already in the meantime finished by the beneficiaries themselves. Deadline: 45 days from the commencement of the works |
| Obrenovac | Over 0.5M EUR. About 90% of all the works finished in Obrenovac in Brace Jugovic settlement. Each house started except those with large damages that have been assessed by the Floods Office and re-categorized into category 6. The deadline in mid-December set and achievable. | Commencement of the works in the first week of October. About 107 houses, small and medium repairs. Deadline: 60 days from the commencement of the works. Additional houses to be selected for small and medium repairs. The municipality Obrenovac sent the list of 90 households; to be selected about 30-40 houses for the most vulnerable families for repairs. |
| Obrenovac, Lazarevac temporary shelters | Procurement procedure for Obrenovac done. Equipment for the temporary shelter has almost been delivered in total. Living conditions will be improved before the Winter starts. | Temporary shelters’ living conditions improved before the winter in both Lazarevac and Obrenovac. |

Date of Update: 18 December 2014

Implementing Partner: UNOPS

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| 16 Local Self-Governments | The construction of first three houses in Obrenovac is completed, while additional four will be finalized during the next week. The construction process on 61 houses is underway. This includes provision of 60, 80 and 100 square metres dwellings to the affected families. The completion of works is expected during Decemeber and January 2015. |  |

Date of Update: 18 December 2014

Implementing Partner: FAO

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| All 24 municipalities | Tendering process for procurement of animal feed (for cows, pigs and poultry-layers) is completed. Delivery of animal feed is expected to start from the week of 22 December 2014 and completed by mid-January. | In period December 2014 - mid-January 2015, animal feed will be delivered to more than 1,600 agriculture producers. Each producer will receive 320 kilograms of animal (cattle, poultry and pig) feed. |
| All 24 municipalities | Tender for procurement of milking equipment for more than 25 agriculture producers is launched. Potential vendors are invited to submit their bids for this kind of agricultural equipment, and the deadline for submitting the offers is 5 January 2015. | During January 2015 milking equipment will be delivered to milk producers who requested this kind of support to re-start their production. |
| All 24 municipalities | Tender for procurement of fertilizer for spring cropping season is launched. Potential vendors are invited to submit their bids with the deadline as 29 December 2014. | Spring crops and fertilizer will be delivered to more than 7,800 beneficiary families during the period early February till end March 2015. Each beneficiary will receive 400 kilograms of NPK fertilizer (for sowing maize, peas, lucerne and red clover), barley producers will receive 300 kilograms each. |
| All 24 municipalities | Tender document for procurement of spring crops seed (barley, peas, red clover, lucerne and maize) for more than 7,800 agriculture producers is being finalized. Tender will be issued by the end of December 2014. | Spring crops and fertilizer will be delivered to beneficiary families during the period early February till end of March 2015. In terms of number of beneficiaries, this will be the largest group receiving support under the EU flood recovery programme. |