29 January 2015

WEEKLY COMMUNICATIONS UPDATE

Overview

- The EU Ambassador Michael Davanport maked the completion of the reconstruction of the Elementary School “Jovan Jovanović Zmaj“. The European Union funded the reconstruction of this school and provided the furniture in the amount of some 216,000 Euros. The rehabilitation of 15 classrooms, gym, library, kitchen and the dining room, six administrative offices and the archive enabled normal conditions for learning to 1,350 pupils. The works included plastering, flooring, replacement of the damaged internal joinery, rehabilitation of the external windows and doors, dismantling and painting of the radiators as well as replacement of the valves in the ground floor. In addition, all electrical installations on the ground floor; equipment in the heating substation and some 200 metres of the surrounding fence were replaced and the facade was rehabilitated.

- Seventy-seven houses in Obrenovac, Krupanj, Svilajnac, Varvarin, Paraćin, Gornji Milanovac, Bajina Bašta, Šid, Smederevo, Smederevska Palanka, Loznica, Ruma  and Mionica have been constructed, while 685 flood affected homes have been rehablitated in Obrenovac, Krupanj, Kraljevo, Lazarevac, Svilajnac, Trstenik, Varvarin, Valjevo, Mali Zvornik, Ljubovija, Šabac, Bajina Bašta, Šid, Loznica, Smederevska Palanka, Velika Plana, Čačak, Ub, Koceljeva, Jagodina and Paraćin. The construction works are in the finishing stage on some 40 family houses. This is the part of private housing reconstruction process for the total of some 950 in 30 municipalities funded through the European Union Assistance for Flood Relief in Serbia Programme which is well underway.

Date of Update: 29th of January 2015

Implementing Partner: ASB/HC/IDC/DIVAC

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Valjevo | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 16 Housing Units reconstruction: Works on 16 houses is completed and handover procedures started. Handover procedure will be completed by the end of January/beginning of February 2015 - 9 new brick Housing Units: on 6 houses construction works are ongoing. Completion of construction works is planned for March/April 2015 according to the weather conditions. Plan for the next week - Start the distribution of furniture and appliances - Monitor construction works and start handover procedures for reconstruction - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Osecina | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 25 Housing Units reconstruction: Works on 20 houses completed; 5 houses are in finishing phase and should be completed at the beginning of February depending on the weather conditions. Finishing of reconstruction works planned within approx 1/2 weeks. Plan for the next week - Start the distribution of furniture and appliances - Monitor reconstruction works and start handover procedure - Monitor beneficiaries who received IG Grants and building material | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Mali Zvornik | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 15 Housing Units reconstruction: Works on 15 houses is completed and handover procedures are completed. - 1 new Housing Unit: Works are in finishing phase (95%), connection to the electrical network has been done; construction of septic tanks still needs to be done. Finishing of construction works planned by the end of January/beginning of February 2015. Plan for the next week - Start the distribution of furniture and appliances - Monitor construction work and start handover procedure for construction work - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljubovija | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 17 Housing Units reconstruction: Works on 17 houses is completed and handover procedures are completed. - 6 Housing Units construction: Works are in finishing phase for 5 houses, connection to the electrical network still needs to be done and construction of septic tanks have been built; 1 house due to weather conditions will be completed by March/April 2015. Finishing of construction works planned within approx 2 weeks. - Distribution of appliances completed to project beneficiaries Plan for the next week - Preparation and distribution of furniture - Monitor construction works and start handover procedures for construction - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sabac | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 27 Housing Units reconstruction: works on 27 houses are finished. Handover procedure will be completed by the end of January/beginning of February 2015 - 1 new Housing Unit construction: works are ongoing Finishing of construction works planned by March/April 2015, according to weather conditions. Economic Component - Continue the distribution of IG Grants. Plan for the next week - Start the distribution of furniture and appliances - Continue handover procedures for reconstruction and prepare construction work - Monitor beneficiaries who received IG Grants and building material - Complete distribution of IG Grants | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) |
| Bajina Basta | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on all houses are finished and handover procedures started Handover procedure will be completed at the beginning of February 2015 - 5 Housing Units construction: Construction of 5 houses is finished: all houses are connected to the electrical network; construction of septic tanks still needs to be done. Finishing of construction works planned within approx 2 weeks. - Distribution of appliances completed to project beneficiaries Plan for the next week - Preparation and distribution of furniture - Continue handover procedures for reconstruction and construction works - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sid | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on 8 houses are finished; works on 14 houses are in finishing phase (Deadline for finishing of works moved due to weather conditions and humidity by the end of January/beginning of February 2015). - 5 Housing Units construction: Construction works are completed in all 5 houses, connection to the electrical network and construction of septic tanks still needs to be done Plan for the next week - Start the distribution of furniture and appliances - Monitor reconstruction and construction works and continue with handover procedures | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) |
| Loznica | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 20 Housing Units reconstruction: Works on 20 houses are finished and handover procedures are ongoing Handover procedure will be completed by the end of January/beginning of February 2015 - 9 Housing Units construction: interior works are in progress, 6 houses planned for finishing by the end of January/beginning of February 2015 due to weather conditions; - 3 additional houses: for 2 houses concrete foundation and solid ground floor is made, and for 1 house works are in progress; for all three houses deadline planned for finishing approximately is March 15th. Plan for the next week - Start the distribution of furniture and appliances - Monitor reconstruction and construction works and continue with handover procedures - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljig | Housing Component - Construction and building of 1 new house - 1 Housing Unit construction: Engineer field visit for the preparation of construction work for the new prefabricated house. Planning is ongoing |  |

Date of Update: 30/01/2015

Implementing Partner: Danish Refugee Council – DRC with Eneca

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR FINAL BENEFICIARIES INCLUDING THE END TIMEFRAME |
| --- | --- | --- |
| Smederevska Palanka | - Reconstruction of individual housing objects (DRC): - The reconstruction of 20 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Field assessments of potential beneficiary households. Preparation of the Beneficiary Selection Process. | All 20 houses completely reconstructed. The number of additional 8 beneficiary families will be assisted in reconstruction of their floods affected households. |
|  | - Construction of prefabricated houses (DRC): - The installation process is completed on all 3 planned prefabs. Tentative plan for the next week: - Advanced phase of interior works in all three prefabs. | All three prefabs installed with ongoing internal electrical, painting and flooring works. Preparation for infrastructure connections. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. Tentative plan for the next week: - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 23 beneficiaries of reconstructed and constructed houses. |
|  | - IGA component (Eneca): Preparation of economic grant delivery. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 3 floods affected business entities realised enhancing the recuperation of their business activities. |
| Velika Plana | - Reconstruction of individual housing objects (DRC): - The reconstruction process finalized in all 12 housing objects. | All 12 houses fully reconstructed and supervision/ handover process realised. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. Tentative plan for the next week: - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 12 beneficiaries of reconstructed houses. |
|  | - IGA component (Eneca): Preparation of economic grant delivery. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 2 floods affected business entities realised enhancing the recuperation of their business activities. |
| Cacak | - Reconstruction of individual housing objects (DRC): - The reconstruction process finalized in all 14 houses. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Field assessments of potential beneficiary households. Preparation of the Beneficiary Selection Process. | All 14 houses fully reconstructed and supervision/ handover process realised. The number of additional 5 beneficiary families will be assisted in reconstruction of their floods affected households. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. - Tentative plan for the next week: - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 14 beneficiaries of reconstructed houses. |
|  | - IGA component (Eneca): Preparation of economic grant delivery. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 1 flood affected business entity realised enhancing the recuperation of its business activities. |
| UB | - Reconstruction of individual housing objects (DRC): - The reconstruction of 23 houses is in the completion phase. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Field assessments of potential beneficiary households. Preparation of the Beneficiary Selection Process. | 22 out of 23 houses completely reconstructed, while the remaining one will be finalised in the following week of Feb 2015. The number of additional 8 beneficiary families will be assisted in reconstruction of their floods affected households. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliance and furniture is ongoing. | Household appliance sets delivered to all 23 beneficiary families, while the furniture sets will be launched in the first weeks of Feb 2015. |
|  | - IGA component (Eneca): Delivery of economic grants Tentative plan for the next week: Delivery and monitoring of realised activities. | First set of 10 out of 20 deliveries of business equipment realised. |
| Koceljeva | - Reconstruction of individual housing objects (DRC): - The reconstruction of 25 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Field assessments of potential beneficiary households. Preparation of the Beneficiary Selection Process. | All 25 houses completely reconstructed. The number of additional 5 beneficiary families will be assisted in reconstruction of their floods affected households. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliances and furniture is ongoing. Tentative plan for the next week: - Monitoring of realised activities. | Household appliance sets delivered to all 25 beneficiary families, while the delivery of furniture sets will be launched in the first weeks of Feb 2015. |
|  | - IGA component (Eneca): Preparation of economic grant delivery. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of business equipment to 4 business entities launched in the first weeks of Feb 2015. |
| Jagodina | - Reconstruction of individual housing objects (DRC): The reconstruction of 33 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Field assessments of potential beneficiary households. Preparation of the Beneficiary Selection Process. | All 33 houses completely reconstructed. The number of additional 15 beneficiary families will be assisted in reconstruction of their floods affected households. |
|  | - Construction of prefabricated houses(DRC): - The construction site has been prepared and the administrative conditions have been realized enabling the commencement of construction works by the end of January 2015. | Preparation of prefab elements finalized. |
|  | - Provision of household appliances and furniture sets (DRC): - Ongoing delivery of home appliances Tentative plan for the next week: - Delivery of furniture and monitoring of realised activities. | Basic sets of household appliances delivered to all 33 reconstructed houses, while the delivery of furniture sets will be launched in the first week of Feb 2015. |
| Paracin | - Reconstruction of individual housing objects (DRC): The reconstruction of 43 houses is in the completion phase. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Field assessments of potential beneficiary households. Preparation of the Beneficiary Selection Process. | 41 out of 43 houses completely reconstructed, while the remaining will be finalised by the end of the following week. The number of additional 20 beneficiary families will be assisted in reconstruction of their floods affected households. |
|  | - Construction of prefabricated houses (DRC): - The installation process of 9 houses is completed. Ongoing preparatory process for the construction of 5 prefab units. Tentative plan for the next week: - Monitoring of realized works. - Preparatory activities for the construction of prefabs. | 9 out of 10 houses installed and preparations for infrastructure connections in process. The number of additional 5 EV families will be assisted in construction of prefab units. |
|  | - Provision of household appliances and furniture sets (DRC): - Ongoing delivery of household appliances and furniture sets for 53 reconstructed and constructed housing objects. Tentative plan for the next week: - Delivery and Monitoring of realized activities. | Basic sets of household appliances and furniture delivered to all 53 reconstructed and constructed houses in Paracin by the end of the following week. |
|  | - IGA component (Eneca): Ongoing delivery of business equipment. Tentative plan for the next week: Delivery and Monitoring of realised activities. | Deliveries of business equipment to 24 business entities launched on 30 Jan 2015. |

Date of Update:	29 January 2015

Implementing Partner:	Help – Hilfe zur Selbsthilfe e.V.

Overview:

Reconstruction works:

Total budget available 780.000,00 EUR

Total to be reconstructed 160 (51 first lot, 94-second lot and 15 additional)

Works on 98 structures (15 Kraljevo, 30 Lazarevac, 37 Svilajnac, 10 Trstenik and 6 Varvarin) finished.

Prefabricated houses:

Total budget available: 300.000,00 EUR

Value of works in progress: 298.490,00 EUR

Value of works for additional houses: 100.000,00 EUR

Initially planned 15, total to be built 20 houses due to the savings in procurement (11 Svilajnac, 1 Varvarin, 1 Ljig, 3 Smederevo, 1 Prolom Banja, Kursumlija, 3 Lazarevac).   Construction works finished on 9 houses and connection to the infrastructure is in progress. Additional 3 houses in Svilajnac have been erected, under the roof, interior works in progress, three more in Lazarevac in the stage of finishing concrete works to base floor slab.

Household appliances and furniture:

Total budget available 290.000,00 EUR

Furniture: cca 170.000,00 EUR

Appliances: cca 130.000,00  EUR

Average set value cca 2.000,00 EUR

Primarily foreseen 135 for assistance in the form of furniture and/or household appliances sets was raised to 180 due to the savings in procurement procedures. First household appliances were delivered in Kraljevo on 28 January for 18 beneficiaries. Distribution of appliances and furniture is in progress for other municipalities/cities as well.

Income generation activities:

Total budget available: 594.000,00 EUR

Number of foreseen 108, total number to be supported 168 .

39800 raspberry seedlings were delivered in November 2014 in Kosjeric. Tender procedures finished, contracts signing with suppliers in progress, delivery expected to begin by the end of February 2015.

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT ANDa) STAGE OF COMPLETION AND b)TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| KRALJEVO | Reconstruction works on 15 houses completely finished, three houses handover in progress between Help and the Contractor. Household appliances for 18 families delivered on 28 January 2015. Furniture delivery due to begin next week in Kraljevo. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 10 homes repaired and at least 10 families provided with the basic furniture and household appliances. At least 20 micro and small business provided with equipment, spare parts and business facilities renovated. |
| KOSJERIC | On 3 November 12 beneficiaries in Kosjeric, village SecaReka received 39800 raspberry seedlings. Value of the assistance: cca 11.000,00 EUR (1313400 dinara). | At least 10 micro and small businesses supported by the raspberry seedlings, equipment spare parts and renovated business facilities. |
| LAZAREVAC | Reconstruction works on 30 houses completely finished including the handover between Help and Contractor. House painting and joinery painting works in progress on remaining 3 houses. Three additional prefabricated houses are in the stage of finishing concrete works to base floor slab. Household appliances and furniture delivery due to begin mid of February. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 30 families provided with the construction material sets and priority works; at least 36 beneficiaries provided with the basic furniture and household appliances, at least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| SVILAJNAC | Reconstruction works on 37 houses have been completely finished while, works on 37 houses in the final phase, completion expected mid of February. Additional 16 houses reconstruction due to begin by the end of February. Eight prefabricated houses are completely finished and connection to the local infrastructure in progress. Three houses have been erected and interior works in progress. Household appliances and furniture delivery due to begin in February. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 70 construction material sets with priority works delivered; At least 78 sets of basic furniture and household appliances supplied,eight families provided with the prefabricated houses; At least 23 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| TRSTENIK | Reconstruction works on 10 houses are completely finished. Final works in form of finishing house painting and mending. Final handover with the Contractor in progress. Delivery of household appliances and furniture due to begin by the mid of February 2015. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 5 households supported by the construction material sets with priority works, At least 5 households provided with the basic furniture and appliances sets, At least 15 micro and small businesses provided with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| VARVARIN | Reconstruction of 6 houses completely finished. Connection to the local infrastructure of prefabricated house in Varvarin is in progress. Delivery of household appliances and furniture due to begin by the mid of February 2015. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 5 families supported by the construction material sets with priority works. At least 6 families supported by the basic furniture and household appliances. One family supported by provision of prefabricated house, At least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |

Date of Update: 29 Jan 2015

Implementing Partner: UNOPS

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| 16 Local Self-Governments | The construction of 38 houses in Obrenovac, Gornji Milanovac, Krupanj, Šid, Ruma, Loznica, Smederevo and Mionica is completed. The construction process on 28 houses is well underway. This includes provision of 60, 80 and 100 square metres dwellings to the affected families. The completion of works is expected during January and February 2015. |  |
| Obrenovac | The EU Ambassador Michael Davanport maked the completion of the reconstruction of the Elementary School „Jovan Jovanović Zmaj“. The European Union funded the reconstruction of this school and provided the furniture in the amount of some 216,000 Euros. The rehabilitation of 15 classrooms, gym, library, kitchen and the dining room, six administrative offices and the archive enabled normal conditions for learning to 1,350 pupils. The works included plastering, flooring, replacement of the damaged internal joinery, rehabilitation of the external windows and doors, dismantling and painting of the radiators as well as replacement of the valves in the ground floor. In addition, all electrical installations on the ground floor; equipment in the heating substation and some 200 metres of the surrounding fence were replaced and the facade was rehabilitated. |  |
| Trstenik | The rehabilitation of three filtration lakes which provide water supply to 15,000 inhabitants of Trstenik is underway. This includes removal of the mud, regulation of the banks and placement of new layers of filtration sand. Rehabilitation of one lake is fully completed, while the works are well in progress on other two. The completion of this intervention funded by the EU with some 192,000 Euros is expected during February 2015. |  |

Date of Update: 29/01/2015

Implementing Partner: IOM

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Krupanj | About 0.2 M investment. 165 houses repaired. Cleaning works done and complaint works underway. | Commencement of the works in the first week of October. 198 houses to be repaired, but some houses already in the meantime finished by the beneficiaries themselves. Deadline: 50 days from the commencement of the works extended to mid-December |
| Obrenovac | Over 0.5M EUR investment. Selection of the additional up to 40 beneficiaries underway and to be completed by the end of January. Over 100 potential beneficiaries to be interviewed. All 110 houses in Obrenovac settlement Brace Jugovic are repaired and prepared for the Winter period at the end of December, except those with large damages that have been assessed by the Floods Office and re-categorized into category 6. Finishing, cleaning and complaint works underway. | Commencement of the works in the first week of October. Total of 110 houses, small and medium repairs. Deadline: 83 days from the commencement of the works. Additional houses to be selected for small and medium repairs. The municipality Obrenovac sent the list of 90 households; up to 40 houses to be selected for the most vulnerable families for repairs. |
| Obrenovac, Lazarevac temporary shelters | Equipment for the temporary shelter has almost been delivered in total. Room, kitchen, sanitary and heating equipment provided. Additional measures taken in order to ensure the safety of the installed equipment. Living conditions improved for the Winter start. | Temporary shelters’ living conditions improved before the winter in both Lazarevac and Obrenovac. |

Date of Update: 29 January 2015

Implementing Partner: FAO

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| All 24 municipalities | Tender for procurement of spring cropping season is finalized on January 10, 2015. Delivery of spring crops will start in mid-February and will continue throughout March 2015. | By the end of March 2015, more than 7,800 agriculture producers will receive spring crops seed (barley, peas, red clover, lucern and maize). In terms of number of beneficiaries, this will be the largest group receiving support under the EU flood recovery programme. |
| All 24 municipalities | Tenders for milking equipment and fertilizers are also closed and vendors are chosen. During February 2015, milking equipment will be delivered to more than 25 farmers, while fertilizer will be delivered to producers within spring crops packages. | By the end of march 2015, more than 7,800 farmers will receive spring crops and milking equipment packages. |