26 February 2015

WEEKLY COMMUNICATIONS UPDATE

Overview

- The rehabilitation of three infiltration lakes which provide water supply to 15,000 inhabitants of Trstenik is completed. This included removal of the mud, regulation of the banks and placement of new layers of filtration sand. This intervention was funded by the EU with some 192,400 Euros. As the part of the standard procedure, the Public Utility Company “Water Supply” now has to obtain three positive findings of the consecutive chemical analysis of the water samples before including lakes back to the system.

- Distribution of spring crops for 7,763 farming families started on 23 February 2015 throughout flood affected areas.  Barley, peas, red clover, lucerne and maize will be delivered to agricultural producers by the end of March with appropriate fertilizers	. More than 3,700 agricultural producers will receive barley, peas, red clover and Lucerne by the end of February, while another 3,700 farmers will receive maize seeds in March. This will be the largest group of agriculture beneficiaries receiving support under the EU Assistance for Flood Relief in Serbia Programme.

- So far, 100 houses in Obrenovac, Krupanj, Svilajnac, Varvarin, Paraćin, Gornji Milanovac, Bajina Bašta, Šid, Malo Crniće, Valjevo, Osečina, Smederevo, Smederevska Palanka, Požega, Loznica, Ruma  and Mionica have been constructed, while 716 flood affected homes have been rehablitated in Obrenovac, Krupanj, Kraljevo, Lazarevac, Svilajnac, Trstenik, Varvarin, Valjevo, Mali Zvornik, Ljubovija, Šabac, Bajina Bašta, Šid, Loznica, Smederevska Palanka, Velika Plana, Čačak, Ub, Koceljeva, Jagodina and Paraćin. The construction works are in the finishing stage on some 30 family houses. This is the part of private housing reconstruction process for the total of some 950 in 30 municipalities funded through the European Union Assistance for Flood Relief in Serbia Programme which is well underway. Parallel to this, basic sets of furniture and home appliances are being deliviered to the flood affected families.

Date of Update: 26th of February 2015

Implementing Partner: ASB/HC/IDC/DIVAC

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Valjevo | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 16 Housing Units reconstruction: Works on 16 houses is completed and handover procedure has been completed. - 9 new brick Housing Units: on 8 houses construction works are ongoing; 1 house still works did not start. Completion of construction works is planned for March/April 2015 according to the weather conditions. - Distribution of furniture and appliances has been completed except for the 9 brick houses in construction Plan for the next week - Continue to monitor construction works - Monitor beneficiaries who received IG Grants, building material/furniture and appliances | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Osecina | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 25 Housing Units reconstruction: Works on all 25 houses are completed; handover procedures have been fully completed. Plan for the next week - Monitor beneficiaries who received IG Grants, building material/furniture and appliances | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Mali Zvornik | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 15 Housing Units reconstruction: Works on all 15 houses is completed and handover procedures are completed. - 1 new Housing Unit: Works are completed, connection to the electrical network has been done; construction of septic tanks is in progress. Handover procedure should be completed in by the 10th of March 2015. Plan for the next week - Start the distribution of furniture and appliances - Monitor construction work and start handover procedure for construction work - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljubovija | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 17 Housing Units reconstruction: Works on 17 houses are completed and handover procedures are completed. - 6 Housing Units construction: Works on 5 houses are completed (pavement is missing only in one house). Construction Connection to the infrastructures should be concluded by the end of the next week; 1 house due to weather conditions will be completed by March 2015. Construction works are in progress. Handover procedure should be completed by the 10th of March 2015. - Distribution of appliances to project beneficiaries is completed Plan for the next week - Monitor construction works and start handover procedures for construction - Monitor beneficiaries who received IG Grants, building material/furniture and appliances | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sabac | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 27 Housing Units reconstruction: works on 27 houses are finished. Handover procedure is completed. - 1 new Housing Unit construction: Act on the 6th category is yet to be issued by the municipality for one house in this municipality. House construction doesn’t start yet. - Completed distribution of appliances for beneficiaries Plan for the next week - Prepare construction works for 1 new prefabricated house after receiving the act of category 6. - Monitor beneficiaries who received IG Grants, building material/furniture and appliances | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) |
| Bajina Basta | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on all houses are finished and handover procedures are completed. - 5 Housing Units construction: Construction of 5 houses is finished: all houses are connected to the electrical network; construction of septic tanks is in progress and should be completed by the next week. Handover procedure should be completed by the 10th of March 2015. Plan for the next week - Continue handover procedures for construction works - Monitor beneficiaries who received IG Grants and building material/furniture and appliances | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sid | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on all 22 houses are completed and handover procedures is completed - 5 Housing Units construction: Construction works are completed in all 5 houses, connection to the electrical network should be completed by the next week. Handover procedure should be completed by the 10th of March 2015 for all houses. - Distribution of appliances is completed Plan for the next week - Monitor construction works and continue with handover procedures - Monitor beneficiaries who received furniture and appliances | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) |
| Loznica | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 20 Housing Units reconstruction: Works on 20 houses are finished and handover procedures are completed - 6 Housing Units construction: works in all 6 houses are completed. Connection to the electrical network and sewerage and water network are completed; Handover procedure should be completed by the 10th of March 2015 for all houses. - 3 additional houses: works are in progress; all three planned for finishing approximately by March 15th; construction of septic tanks still needs to be done. Plan for the next week - Monitor construction works and continue with handover procedures - Monitor beneficiaries who received IG Grants building material/furniture and appliances | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljig | Housing Component - Construction and building of 1 new house - 1 Housing Unit construction: preparation works are ongoing. Plan for the next week - Beginning of the construction works (according to weather conditions) |  |

Date of Update: 26/02/2015

Implementing Partner: Danish Refugee Council – DRC with Eneca

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR FINAL BENEFICIARIES INCLUDING THE END TIMEFRAME |
| --- | --- | --- |
| Smederevska Palanka | - Reconstruction of individual housing objects (DRC): - The reconstruction of 20 houses is completed. - The Final List of 8 beneficiaries selected for additional assistance in reconstruction of individual housing objects was publicized on the municipal information board 19 Feb 2015. Tentative plan for the next week: Preparatory activities for commencement of reconstruction works. | All 20 houses completely reconstructed. The number of additional 8 beneficiary families will be assisted in reconstruction of their floods affected households to be starting from 9 March 2015 onwards. |
|  | - Construction of prefabricated houses (DRC): - The installation process is completed on all 3 planned prefabs. Tentative plan for the next week: - Preparation for infrastructure connections. | All three prefabs installed and interior works realised. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 23 beneficiaries of reconstructed and constructed houses. |
|  | - IGA component (Eneca): Economic grant delivery is in the finishing phase. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 3 floods affected business entities realised enhancing the recuperation of their business activities. |
| Velika Plana | - Reconstruction of individual housing objects (DRC): - The reconstruction process finalized in all 12 housing objects. | All 12 houses fully reconstructed and supervision/ handover process realised. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 12 beneficiaries of reconstructed houses. |
|  | - IGA component (Eneca): Economic grant delivery is in the finishing phase. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 2 floods affected business entities realised enhancing the recuperation of their business activities. |
| Cacak | - Reconstruction of individual housing objects (DRC): - The reconstruction process finalized in all 14 houses. - The Final List of 5 beneficiaries selected for the additional assistance in reconstruction of individual housing objects was publicized on the municipal information board 24 Feb 2015. Tentative plan for the next week: Preparatory activities for the commencement of construction works. | All 14 houses fully reconstructed and supervision/ handover process realised. The number of additional 5 beneficiary families will be assisted in reconstruction of their floods affected households to be starting from 9 March 2015 onwards. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 14 beneficiaries of reconstructed houses. |
|  | - IGA component (Eneca): Economic grant delivery is in the finishing phase. Tentative plan for the next week: Monitoring of realised activities. | Deliveries of equipment to 1 flood affected business entity realised enhancing the recuperation of its business activities. |
| UB | - Reconstruction of individual housing objects (DRC): - The reconstruction of 23 houses is completed. - The Final List of 8 beneficiaries selected for the additional assistance in reconstruction of individual housing objects was publicized on the municipal information board 20 Feb 2015. Tentative plan for the next week: - Preparatory activities for the commencement of construction works. | All 23 houses completely reconstructed. The number of additional 8 beneficiary families will be assisted in reconstruction of their floods affected households to be starting from 9 March 2015 onwards. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Household appliance and furniture sets delivered to all 23 beneficiary families. |
|  | - IGA component (Eneca): Economic grant delivery is in the finishing phase. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to all 20 flood affected business entities realised enhancing the recuperation of its business activities. |
| Koceljeva | - Reconstruction of individual housing objects (DRC): - The reconstruction of 25 houses is completed. - The Final List of 5 beneficiaries selected for the additional assistance in reconstruction of individual housing objects will be publicized upon completion of complaint period. Tentative plan for the next week: - Preparatory activities for the commencement of construction works. | All 25 houses completely reconstructed. The number of additional 5 beneficiary families will be assisted in reconstruction of their floods affected households to be starting from 9 March 2015 onwards. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliances and furniture is ongoing. Tentative plan for the next week: - Monitoring of realised activities. | Household appliance and furniture sets delivered to all 25 beneficiary families. |
|  | - IGA component (Eneca): Economic grant delivery is in the finishing phase. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to all 4 flood affected business entities realised enhancing the recuperation of its business activities. |
| Jagodina | - Reconstruction of individual housing objects (DRC): The reconstruction of 33 houses is completed. - The Final List of 15 beneficiaries selected for the additional assistance in reconstruction of individual housing objects was publicized on the municipal information board 24 Feb 2015. Tentative plan for the next week: Preparatory activities for the commencement of construction works. | All 33 houses completely reconstructed. The number of additional 15 beneficiary families will be assisted in reconstruction of their floods affected households to be starting from 9 March 2015 onwards. |
|  | - Construction of prefabricated houses(DRC): - The construction site has been prepared, however new findings regarding location conditions have not proved positive. Ongoing allocation of a plot of land for construction. | Preparation of prefab elements finalized. |
|  | - Provision of household appliances and furniture sets (DRC): Monitoring of realised activities. Tentative plan for the next week: Monitoring of realised activities. | Basic sets of household appliances and furniture delivered to all 33 reconstructed houses. |
| Paracin | - Reconstruction of individual housing objects (DRC): The reconstruction of 43 houses is completed. The Final List of 15 beneficiaries selected for the additional assistance in reconstruction of individual housing objects was publicized on the municipal information board 24 Feb 2015. Tentative plan for the next week: - Preparatory activities for the commencement of construction works. | All 43 houses completely reconstructed. The number of additional 20 beneficiary families will be assisted in reconstruction of their floods affected households to be starting from 9 March 2015 onwards. |
|  | - Construction of prefabricated houses (DRC): - Construction process of 9 houses finalised. Ongoing construction of 1 prefab. Ongoing preparatory process for construction of 5 prefab units. Tentative plan for the next week: - Monitoring of realized works. - Preparatory activities for the commencement of construction works. | 9 houses installed and ready for the families’ move-in. Construction of 1 remaining prefab house commenced. The number of additional 5 EV families will be assisted in construction of prefab units. Construction works on additional 5 prefabs are expected to commence from the end of Feb 2015 onwards. |
|  | - Provision of household appliances and furniture sets (DRC): - Delivery of household appliances and furniture sets to 53 beneficiary families is in the finishing phase. Tentative plan for the next week: - Monitoring of realized activities. | Basic sets of household appliances and furniture delivered to all 53 reconstructed and constructed houses. |
|  | - IGA component (Eneca): Economic grant delivery is in the finishing phase. Tentative plan for the next week: Delivery and Monitoring of realised activities. | Deliveries of business equipment to 24 business entities realised by mid Feb 2015. |

Date of Update:	26 February 2015

Implementing Partner:	Help – Hilfe zur Selbsthilfe e.V.

Overview:

Reconstruction works:

Total budget available 780.000,00 EUR

Total to be reconstructed 160 (51 first lot, 94-second lot and 15 additional)

Reconstruction works finished on 107 houses (18 Kraljevo, 33 Lazarevac, 37 Svilajnac, 13 Trstenik and 6 Varvarin).

Prefabricated houses:

Total budget available: 300.000,00 EUR

Initially planned 15, total to be built 20 houses due to the savings in procurement (11 Svilajnac, 1 Varvarin, 1 Ljig, 3 Smederevo, 1 Prolom Banja, Kursumlija, 3 Lazarevac).

Construction works finished on 9 houses, 7 under construction and 4 (3 in Smederevo and 1 in Prolom Banja) pending commencement of construction activities

Household appliances and furniture:

Total budget available 290.000,00 EUR

Furniture: cca 170.000,00 EUR

Appliances: cca 130.000,00  EUR

Primarily foreseen 135 furniture and/or household appliances sets increased to 180 due to the savings in procurement procedures.

Distribution of household appliances finished for 68 households 9 in Trstenik, 18 in Kraljevo, 7 in Varvarin, 24 in Svilajnac and 10 in Lazarevac and still ongoing, furniture delivered for 23 households 20 in Kraljevo and 3 in Svilajnac, and ongoing.

Income generation activities:

Total budget available: 594.000,00 EUR

Foreseen number of IGA beneficiaries 108, total number to be supported 168.

39800 raspberry seedlings were delivered in November 2014 in Kosjeric.

The equipment delivery begun in the week of 23 February 2015 with delivery of greenhouse film and plastic, pipes and connectors for greenhouses and is ongoing as well as the delivery of equipment for micro and small businesses (tools and machinery).

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND a) STAGE OF COMPLETION AND b)TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| KRALJEVO | Reconstruction works on all 18 houses finished. Household appliances delivered for 18 families and furniture for 20 families. Value of furniture 19.791.00 EUR. IGA assistance in equipment and greenhouses - ongoing. | At least 10 homes repaired and at least 10 families provided with the basic furniture and household appliances. At least 20 micro and small business provided with equipment, spare parts and business facilities renovated. |
| KOSJERIC | On 3 November 12 beneficiaries in Kosjeric, village Seca Reka received 39800 raspberry seedlings. Value of the assistance: cca 11.000,00 EUR (1313400 dinara). | At least 10 micro and small businesses supported by the raspberry seedlings, equipment spare parts and renovated business facilities. |
| LAZAREVAC | Reconstruction works on 33 family houses finished. Prefabricated houses: One duplex prefabricated house for two single parent families is assembled and thermal insulation and façade finished, interior works ongoing and house painting in progress. One prefabricated house all installation works finished, house painting ongoing. Household appliances delivered to 10 families furniture delivery ongoing. IGA assistance in equipment and greenhouses - ongoing. | At least 30 families provided with the construction material sets and priority works; at least 36 beneficiaries provided with the basic furniture and household appliances, at least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| SVILAJNAC | Reconstruction works finished on 37 houses and works on 37 houses in the process of finishing flooring and handover begun. Additional 16 houses reconstruction due to begin by the end of February. Eight prefabricated houses are completely finished. Three prefabricated houses have been erected and interior works in progress, as well as the facade works. Household appliances and furniture delivery began on 12 February and ongoing. IGA assistance in equipment and greenhouses - ongoing. | At least 70 construction material sets with priority works delivered; At least 78 sets of basic furniture and household appliances supplied, eight families provided with the prefabricated houses; At least 23 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| TRSTENIK | Reconstruction works on 13 houses finished. Household appliances for 9 beneficiaries delivered on 12 February 2015, furniture delivery ongoing. IGA assistance in equipment and greenhouses - ongoing. | At least 5 households supported by the construction material sets with priority works, At least 5 households provided with the basic furniture and appliances sets, At least 15 micro and small businesses provided with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| VARVARIN | Reconstruction of 6 houses finished. Connection to the local infrastructure of 1 prefabricated house built in Varvarin ongoing. Six sets of basic household appliances (ovens, refrigerators, washers, boilers) in value of 7.882,90 EUR delivered on 5 February 2015 IGA assistance in equipment and greenhouses - ongoing. | At least 5 families supported by the construction material sets with priority works. At least 6 families supported by the basic furniture and household appliances. One family supported by provision of prefabricated house, At least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |

Date of Update: 26 February 2015

Implementing Partner: UNOPS

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| 16 Local Self-Governments | The construction of 57 houses in Obrenovac, Gornji Milanovac, Krupanj, Šid, Ruma, Loznica, Smederevo and Mionica is completed. The construction process on 16 houses is well underway. This includes provision of 60, 80 and 100 square metres dwellings to the affected families. The completion of works is expected during March 2015 depending on the weather conditions. |  |
| Trstenik | The rehabilitation of three filtration lakes which provide water supply to 15,000 inhabitants of Trstenik is completed. This included removal of the mud, regulation of the banks and placement of new layers of filtration sand. The completion of this intervention funded by the EU with some 192,400 Euros. As the part of the standard procedure, the Public Utility Company “Water Supply” now has to obtain positive findings of the consecutive chemical analysis of the water samples before including lakes back to the system. |  |

Date of Update: 26 February,2015

Implementing Partner: FAO

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| All 24 municipalities | Distribution of spring crops for 7.763 farming families started on February 23. Spring crops will be delivered to agricultural producers by the end of March (barley, peas, red clover, lucerne and maize), with appropriate fertilizers | More than 3,700 agricultural producers will receive barley, peas, red clover and Lucerne by the end of February, while another 3,700 farmers will receive maize seeds in March. This will be the largest group receiving support under the EU flood recovery programme. |
| All 24 municipalities | Tender procedure for procurement of milking equipment for 28 milk producers has been completed and supplier company selected. | During March 2015, the equipment will be delivered to beneficiaries. |
|  | Tender for procurement of tractor accessories is issued. Potential suppliers are invited to send their offers for procurement of disc harrows, fertilizer spreaders, ploughs, mowers, sprayers...During preparation of the tender documents every single agricultural producer entitled for this support was consulted and priorities of the producers are respected as much as possible. | Tender will be closed on March 02, 2015, and vendor will be chosen by the end of March. During April 2015, tractor accessories will be delivered to 77 farmers in 20 municipalities. |
|  | Tender for procurement of movable machines is issued. Potential suppliers are invited to send their offers for procurement of cultivators, motor hoes and mowers. During preparation of the tender documents every single agricultural producer entitled for this support was consulted and priorities of the producers are respected as much as possible. | Tender will be closed on March 02, 2015, and vendor will be chosen by the end of March. During April 2015, movable machines will be delivered to 43 farmers in 20 municipalities. |
| All 24 municipalities | Tender for procurement of mineral fertilizer for spring cropping season has been completed and vendor selected. Mineral fertilizer will be delivered to 7.763 producers who received spring seeds, so spring crops are sawn in optimal time for sowing. | More than 2.950 tons of fertilizer will be delivered to producers during March 2015. |