5 February 2015

WEEKLY COMMUNICATIONS UPDATE

Overview

- More than 3,700 agricultural producers will receive barley, peas, red clover and Lucerne by the end of February, while another 3,700 farmers will receive maize seeds in March 2015. This will be the timely support for the spring cropping season, which will aim the largest group of agriculture families receiving support through the EU Assistance for Flood Relief Programme. At the same time, more than 120 farming families in Serbia will receive small agriculture equipment such as ploughs, mowers, tillers etc. during next two months.

- The provision of grants to more than 250 micro and small enterprises is underway. The delivery of equipment and raw material for restoring of the income generation activities is being conducted during February 2015. Within this lot, greenhouses will be delivered to the selected agriculture entrepreneurs, while equipment and raw material will be provided to the affected businesses.

- Ninety-three houses in Obrenovac, Krupanj, Svilajnac, Varvarin, Paraćin, Gornji Milanovac, Bajina Bašta, Šid, Malo Crniće, Valjevo, Osečina, Smederevo, Smederevska Palanka, Požega, Loznica, Ruma  and Mionica have been constructed, while 698 flood affected homes have been rehablitated in Obrenovac, Krupanj, Kraljevo, Lazarevac, Svilajnac, Trstenik, Varvarin, Valjevo, Mali Zvornik, Ljubovija, Šabac, Bajina Bašta, Šid, Loznica, Smederevska Palanka, Velika Plana, Čačak, Ub, Koceljeva, Jagodina and Paraćin. The construction works are in the finishing stage on some 30 family houses. This is the part of private housing reconstruction process for the total of some 950 in 30 municipalities funded through the European Union Assistance for Flood Relief in Serbia Programme which is well underway. Parallel to this, basic sets of furniture and home appliances are being deliviered to the flood affected families.

Date of Update: 5th of February 2015

Implementing Partner: ASB/HC/IDC/DIVAC

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Valjevo | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 16 Housing Units reconstruction: Works on 16 houses is completed and handover procedure has been completed. - 9 new brick Housing Units: on 8 houses construction works are ongoing; 1 house still works did not start Completion of construction works is planned for March/April 2015 according to the weather conditions. - Distribution of furniture to project beneficiaries completed Plan for the next week - Distribution of appliances to project beneficiaries - Continue to monitor construction works - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Osecina | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 25 Housing Units reconstruction: Works on all 25 houses are completed; handover procedures are ongoing and will be completed in approximately one week/10 days Plan for the next week - Start the distribution of furniture and appliances - Continue handover procedure for construction works - Monitor beneficiaries who received IG Grants and building material | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Mali Zvornik | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 15 Housing Units reconstruction: Works on all 15 houses is completed and handover procedures are completed. - 1 new Housing Unit: Works are completed (only pavement is missing), connection to the electrical network has been done; construction of septic tanks still needs to be done. Handover procedure will be completed in February 2015. Plan for the next week - Start the distribution of furniture and appliances - Monitor construction work and start handover procedure for construction work - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljubovija | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 17 Housing Units reconstruction: Works on 17 houses is completed and handover procedures are completed. - 6 Housing Units construction: Works on 5 houses are almost completed (pavement is missing, fitting doors). Connection to the electrical network still needs to be done and construction of septic tanks has been built; 1 house due to weather conditions will be completed by March 2015. Finishing of construction works planned within approx 1 week. Handover procedure will be completed in February 2015 for 5 houses. Plan for the next week - Preparation and distribution of furniture - Monitor construction works and start handover procedures for construction - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sabac | Housing Component - Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 27 Housing Units reconstruction: works on 27 houses are finished. Handover procedure will be completed in one week/10 days. - 1 new Housing Unit construction: Act on the 6th category is yet to be issued by the municipality for one house in this municipality. Finishing of construction works planned by March/April 2015. - Distribution of appliances to project beneficiaries completed Economic Component - Completed distribution of IG Grants. Plan for the next week - Distribution of furniture to project beneficiaries - Continue handover procedures for reconstruction and prepare construction works for 1 house - Monitor beneficiaries who received IG Grants and building material | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) |
| Bajina Basta | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on all houses are finished and handover procedures is in progress Handover procedure will be completed in one week/10 days - 5 Housing Units construction: Construction of 5 houses is finished: all houses are connected to the electrical network; construction of septic tanks still needs to be done. Handover procedure will be completed in February 2015 for 5 houses. - Distribution of appliances to project beneficiaries and furniture almost completed Plan for the next week - Continue handover procedures for reconstruction and construction works - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sid | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 22 Housing Units reconstruction: Works on all 22 houses are completed and handover procedures is in progress Handover procedure will be completed in one 2/3 weeks. - 5 Housing Units construction: Construction works are completed in all 5 houses, connection to the electrical network and construction of septic tanks still needs to be done. Handover procedure will be completed in February 2015 for all houses. - Distribution of furniture to project beneficiaries are completed Plan for the next week - Complete distribution of appliances - Monitor reconstruction and construction works and continue with handover procedures | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) |
| Loznica | Housing Component - Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) - 20 Housing Units reconstruction: Works on 20 houses are finished and handover procedures are ongoing Handover procedure will be completed by the end of January/beginning of February 2015. - 6 Housing Units construction: works in all 6 houses are completed. Temporary connection to the electrical network and sewerage and water network will be done till February 15th; - 3 additional houses: works are in progress; all three planned for finishing approximately by March 15th; construction of septic tanks still needs to be done. Plan for the next week - Start the distribution of furniture and appliances - Monitor reconstruction and construction works and continue with handover procedures - Monitor beneficiaries who received IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljig | Housing Component - Construction and building of 1 new house - 1 Housing Unit construction: preparation works are ongoing. |  |

Date of Update: 05/02/2015

Implementing Partner: Danish Refugee Council – DRC with Eneca

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR FINAL BENEFICIARIES INCLUDING THE END TIMEFRAME |
| --- | --- | --- |
| Smederevska Palanka | - Reconstruction of individual housing objects (DRC): - The reconstruction of 20 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Beneficiary Selection Committee for the selection of 8 additional beneficiaries is scheduled for 9 Feb 2015. | All 20 houses completely reconstructed. The number of additional 8 beneficiary families will be assisted in reconstruction of their floods affected households. Reconstruction works on additional 8 households are expected to commence by the end of Feb 2015. |
|  | - Construction of prefabricated houses (DRC): - The installation process is completed on all 3 planned prefabs. Tentative plan for the next week: - Preparation for infrastructure connections. | All three prefabs installed and interior works realised. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 23 beneficiaries of reconstructed and constructed houses. |
|  | - IGA component (Eneca): Economic grant delivery has commenced. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 3 floods affected business entities realised enhancing the recuperation of their business activities. |
| Velika Plana | - Reconstruction of individual housing objects (DRC): - The reconstruction process finalized in all 12 housing objects. | All 12 houses fully reconstructed and supervision/ handover process realised. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 12 beneficiaries of reconstructed houses. |
|  | - IGA component (Eneca): Economic grant delivery has commenced. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of equipment to 2 floods affected business entities realised enhancing the recuperation of their business activities. |
| Cacak | - Reconstruction of individual housing objects (DRC): - The reconstruction process finalized in all 14 houses. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Beneficiary Selection Committee for the selection of 5 additional beneficiaries is scheduled for 10 Feb 2015. | All 14 houses fully reconstructed and supervision/ handover process realised. The number of additional 5 beneficiary families will be assisted in reconstruction of their floods affected households. Reconstruction works on additional 5 households are expected to commence by the end of Feb 2015. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 14 beneficiaries of reconstructed houses. |
|  | - IGA component (Eneca): Economic grant delivery has commenced. Tentative plan for the next week: Monitoring of realised activities. | Deliveries of equipment to 1 flood affected business entity realised enhancing the recuperation of its business activities. |
| UB | - Reconstruction of individual housing objects (DRC): - The reconstruction of 23 houses is in the completion phase. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Beneficiary Selection Committee for the selection of 8 additional beneficiaries is scheduled for 10 Feb 2015. | 22 out of 23 houses completely reconstructed, while the remaining one will be finalised by 10 Feb 2015. The number of additional 8 beneficiary families will be assisted in reconstruction of their floods affected households. Reconstruction works on additional 8 households are expected to commence by the end of Feb 2015. |
|  | - Provision of household appliances and furniture sets (DRC): - Monitoring of realised activities. | Household appliance and furniture sets delivered to all 23 beneficiary families. |
|  | - IGA component (Eneca): Ongoing delivery of economic grants. Tentative plan for the next week: Delivery and monitoring of realised activities. | Set of 15 out of 20 deliveries of business equipment realised. |
| Koceljeva | - Reconstruction of individual housing objects (DRC): - The reconstruction of 25 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Beneficiary Selection Committee for the selection of 5 additional beneficiaries is scheduled for 11 Feb 2015. | All 25 houses completely reconstructed. The number of additional 5 beneficiary families will be assisted in reconstruction of their floods affected households. Reconstruction works on additional 5 households are expected to commence by the end of Feb 2015. |
|  | - Provision of household appliances and furniture sets (DRC): - The delivery of household appliances and furniture is ongoing. Tentative plan for the next week: - Monitoring of realised activities. | Household appliance sets delivered to all 25 beneficiary families, while the delivery of furniture sets will be realised by the end of following week of Feb 2015. |
|  | - IGA component (Eneca): Preparation of economic grant delivery. Tentative plan for the next week: Delivery and monitoring of realised activities. | Deliveries of business equipment to 4 business entities launched in the following week of Feb 2015. |
| Jagodina | - Reconstruction of individual housing objects (DRC): The reconstruction of 33 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Beneficiary Selection Committee for the selection of 15 additional beneficiaries is scheduled for 11 Feb 2015. | All 33 houses completely reconstructed. The number of additional 15 beneficiary families will be assisted in reconstruction of their floods affected households. Reconstruction works are expected to commence by the end of Feb 2015. |
|  | - Construction of prefabricated houses(DRC): - The construction site has been prepared, however new findings regarding location conditions have not proved positive. Ongoing allocation of a plot of land for construction. | Preparation of prefab elements finalized. |
|  | - Provision of household appliances and furniture sets (DRC): Monitoring of realised activities. Tentative plan for the next week: Monitoring of realised activities. | Basic sets of household appliances and furniture delivered to all 33 reconstructed houses. |
| Paracin | - Reconstruction of individual housing objects (DRC): The reconstruction of 42 houses is completed. Ongoing field assessments of additional number of floods affected households to be assisted in reconstruction. Tentative plan for the next week: - Beneficiary Selection Committee for the selection of 20 additional beneficiaries is scheduled for 12 Feb 2015. | 42 out of 43 houses completely reconstructed, while the remaining will be finalised by the end of the following week. The number of additional 20 beneficiary families will be assisted in reconstruction of their floods affected households. Reconstruction works on additional 20 households are expected to commence by the end of Feb 2015. |
|  | - Construction of prefabricated houses (DRC): - The installation process of 9 houses is completed. Ongoing preparatory process for the construction of 5 prefab units. Tentative plan for the next week: - Monitoring of realized works. - Preparatory activities for the construction of prefabs. | 9 out of 10 houses installed and preparations for infrastructure connections in process. The number of additional 5 EV families will be assisted in construction of prefab units. Construction works on prefabs are expected to commence by the end of Feb 2015. |
|  | - Provision of household appliances and furniture sets (DRC): - Delivery of household appliances and furniture sets to 53 beneficiary families is in the finishing phase. Tentative plan for the next week: - Monitoring of realized activities. | Basic sets of household appliances and furniture delivered to all 53 reconstructed and constructed houses in Paracin by 10 Feb 2015. |
|  | - IGA component (Eneca): Ongoing delivery of business equipment. Tentative plan for the next week: Delivery and Monitoring of realised activities. | Deliveries of business equipment to 24 business entities realised by mid Feb 2015. |

Date of Update:	05 February 2015

Implementing Partner:	Help – Hilfe zur Selbsthilfe e.V.

Overview:

Reconstruction works:

Total budget available 780.000,00 EUR

Total to be reconstructed 160 (51 first lot, 94-second lot and 15 additional)

Reconstruction works on 101 houses (15 Kraljevo, 31 Lazarevac, 37 Svilajnac, 12 Trstenik and 6 Varvarin) finished.

Prefabricated houses:

Total budget available: 300.000,00 EUR

Value of works in progress: 298.490,00 EUR

Value of works for additional houses: 100.000,00 EUR

Initially planned 15, total to be built 20 houses due to the savings in procurement (11 Svilajnac, 1 Varvarin, 1 Ljig, 3 Smederevo, 1 Prolom Banja, Kursumlija, 3 Lazarevac).   Construction works finished on nine houses and requests with project documents submitted to EPI for nine houses connection to the infrastructure pending.

Household appliances and furniture:

Total budget available 290.000,00 EUR

Furniture: cca 170.000,00 EUR

Appliances: cca 130.000,00  EUR

Average set value cca 2.000,00 EUR

Primarily foreseen 135 furniture and/or household appliances sets increased to 180 due to the savings in procurement procedures.

First household appliances were delivered in Kraljevo on 28 January for 18 beneficiaries, followed by the distribution of six sets in Varvarin on 5 February 2015. Distribution of appliances and furniture is ongoing.

Income generation activities:

Total budget available: 594.000,00 EUR

Foreseen number of IGA beneficiaries 108, total number to be supported 168.

39800 raspberry seedlings were delivered in November 2014 in Kosjeric. Tender procedures finished, signing contracts with suppliers in progress, delivery expected to begin by the end of February 2015.

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND a) STAGE OF COMPLETION AND b)TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| KRALJEVO | Reconstruction works on 15 houses completely finished, three houses handover in progress between Help and the Contractor. Household appliances for 18 families delivered on 28 January 2015. Furniture delivery pending. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 10 homes repaired and at least 10 families provided with the basic furniture and household appliances. At least 20 micro and small business provided with equipment, spare parts and business facilities renovated. |
| KOSJERIC | On 3 November 12 beneficiaries in Kosjeric, village Seca Reka received 39800 raspberry seedlings. Value of the assistance: cca 11.000,00 EUR (1313400 dinara). | At least 10 micro and small businesses supported by the raspberry seedlings, equipment spare parts and renovated business facilities. |
| LAZAREVAC | Reconstruction works on 31 houses completely finished including the handover between Help and Contractor. House painting on 2 houses ongoing. Prefabricated houses: on two houses finished works on concrete foundation while assembly of prefabricated panels is ongoing. Concrete foundation poured, next week concrete works on base floor slab. Household appliances and furniture delivery due to begin mid of February. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 30 families provided with the construction material sets and priority works; at least 36 beneficiaries provided with the basic furniture and household appliances, at least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| SVILAJNAC | Reconstruction works on 37 houses have been completely finished while, works on 37 houses are in the final phase of flooring and house painting completion expected mid of February. Additional 16 houses reconstruction due to begin by the end of February. Eight prefabricated houses are completely finished and connection to the local infrastructure is in progress. Three prefabricated houses have been erected and interior works in progress, as well as the facade works. Household appliances and furniture delivery due to begin by mid February. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 70 construction material sets with priority works delivered; At least 78 sets of basic furniture and household appliances supplied, eight families provided with the prefabricated houses; At least 23 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| TRSTENIK | Reconstruction works on 12 houses are finished. One house painting and flooring works are in progress. Final handover with the Contractor is ongoing. Delivery of household appliances and furniture due to begin mid of February 2015. IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 5 households supported by the construction material sets with priority works, At least 5 households provided with the basic furniture and appliances sets, At least 15 micro and small businesses provided with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| VARVARIN | Reconstruction of 6 houses completely finished. Connection to the local infrastructure of 1 prefabricated house in Varvarin is in progress. Six sets of basic household appliances (ovens, refrigerators, washers, boilers) in value of 7.882,90 EUR delivered on 5 February 2015 (photos attached) IGA assistance in equipment and greenhouses due to begin by the end of February 2015. | At least 5 families supported by the construction material sets with priority works. At least 6 families supported by the basic furniture and household appliances. One family supported by provision of prefabricated house, At least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |

Date of Update: 5 February 2015

Implementing Partner: UNOPS

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| 16 Local Self-Governments | The construction of 50 houses in Obrenovac, Gornji Milanovac, Krupanj, Šid, Ruma, Loznica, Smederevo and Mionica is completed. The construction process on 16 houses is well underway. This includes provision of 60, 80 and 100 square metres dwellings to the affected families. The completion of works is expected during February 2015 depending on the weather conditions. |  |
| Trstenik | The rehabilitation of three filtration lakes which provide water supply to 15,000 inhabitants of Trstenik is underway. This includes removal of the mud, regulation of the banks and placement of new layers of filtration sand. Rehabilitation of one lake is fully completed, while the works are well in progress on other two. The completion of this intervention funded by the EU with some 192,000 Euros is expected during February 2015. |  |

Date of Update: 05 February 2015

Implementing Partner: FAO

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| All 24 municipalities | Tender for procurement of spring cropping season is closed and vendors are chosen this week. Distribution of barley, Lucerne, red clover and peas starts next week while distribution of maize starts as of 09 March 2015. | More than 3,700 agricultural producers will receive barley, peas, red clover and Lucerne by the end of February, while another 3,700 farmers will receive maize seeds in March. This will be the largest group receiving support under the EU flood recovery programme. |
| All 24 municipalities | Technical documentation for procurement of small agricultural equipment is finalized this week. Tender will be issued in next two weeks. | Small agricultural equipment (ploughs, mowers, tillers,…) is procured for more than 120 farming families in Serbia. Agricultural machinery will be delivered to beneficiaries during next 2 months. |
| All 24 municipalities | FAO team Serbia is starting preparation for tender for procurement of more than 600 greenhouses to beneficiaries whose vegetable production is damaged during May 2014 floods. Experts for greenhouse production are engaged to visit beneficiaries, affected municipalities and greenhouse producers in period 09-13 February 2015. | After assessing situation on the field, FAO team will prepare technical documentation together with greenhouse production experts. Delivery of greenhouses will be start in March and will continue throughout spring 2015 season. |